## Project Planner
Learning Team A Project Planner
| Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
WBS# | ACTIVITY | RESOURCE | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.1 | Work Order Processing
1.1.1 | Review and accept work order from customer |  | 1 | 1 | 1 | 1 | 100%
1.1.2 | Submit Work Order to Finance Department for project funding |  | 1 | 1 | 1 | 1 | 100%
1.1.3 | Secure financing |  | 2 | 1 | 2 | 1 | 100%
1.2 | Phase Brief with customer and project requirements
1.2.1 | Research Aircraft Historical Records and Open/Closed Faults |  | 3 | 1 | 3 | 1 | 100%
1.2.2 | Conduct Phase Brief with owning customer to discuss work requested and project requirements |  | 3 | 1 | 3 | 1 | 100%
1.2.3 | Agree to project terms, such as owning unit support, Estimated Completion Date, and budget goals. |  | 3 | 1 | 3 | 1 | 100%
1.3 | Preparation
1.3.1 | Gather parts POL (preservatives, oils, and lubricants) needed for reassembly of aircraft. |  | 4 | 1 | 4 | 1 | 100%
1.3.2 | Determine hangar/bay the phase inspections will be conducted in. |  | 4 | 1 | 4 | 1 | 100%
1.3.3 | Gather consumables, expendables, tools, and ground support equipment needed to perform phase inspections. |  | 4 | 1 | 4 | 1 | 100%
1.4 | Phase Induction
1.4.1 | Pre-phase Test Flight and Power-on Maintenance Operational Checks |  | 5 | 1 | 5 | 1 | 100%
1.4.2 | Document any faults found during Test Flight and Power-ons |  | 5 | 1 | 5 | 1 | 100%
1.4.3 | Disassemble and wash aircraft for phase inspections. |  | 6 | 3 | 6 | 3 | 100%
1.5 | Inspections
1.5.1 | Inspect components removed for phase inspections |  | 9 | 5 | 9 | 5 | 100%
1.5.2 | Inspect overall airframe |  | 9 | 5 | 9 | 5 | 100%
1.5.3 | Document faults found in aircraft phase books. |  | 9 | 5 | 9 | 5 | 100%
1.5.4 | Confirm inspection results with Technical Inspectors (Quality Control) |  | 9 | 5 | 9 | 5 | 100%
1.6 | Repairs and replacements of faulty components
1.6.1 | Identify needed repairs and components that failed inspections |  | 14 | 1 | 14 | 1 | 100%
1.6.2 | Research that all parts and POL are on available to perform repairs, if unavailable place needed parts/POL on order |  | 14 | 1 | 14 | 1 | 100%
1.6.3 | Perform repairs and replace faulty components |  | 15 | 3 | 15 | 3 | 100%
1.6.4 | Complete required paperwork and quality control confirms repairs are repaired properly |  | 18 | 1 | 18 | 1 | 100%
1.6.5 | Government oversight confirms repairs, including paperwork are completed correctly |  | 18 | 1 | 18 | 1 | 100%
1.7 | Reassembly
1.7.1 | Reassemble the aircraft |  | 19 | 5 | 19 | 5 | 100%
1.7.2 | Update paperwork to reflect aircraft reassembly |  | 19 | 5 | 19 | 5 | 100%
1.7.3 | Quality Control inspects the reassembled aircraft |  | 24 | 1 | 24 | 1 | 100%
1.7.4 | Governement oversight confirms reassembly and paperwork was completed correctly |  | 24 | 1 | 24 | 1 | 100%
1.8 | Power-ons and Maintenance Operational Checks
1.8.1 | Perform power-ons and maintenance operational checks |  | 25 | 1 | 25 | 1 | 100%
1.8.2 | Rig various flight controls and engine power levers |  | 25 | 1 | 25 | 1 | 100%
1.8.3 | Adjust electrical nulls and calibrated flight equipment. |  | 25 | 1 | 25 | 1 | 100%
1.8.4 | Quality Control inspects the rig adjustments and electrical adjustments |  | 26 | 1 | 26 | 1 | 100%
1.8.5 | Governement oversight confirms rig and electrical adjustments |  | 26 | 1 | 26 | 1 | 100%
1.9 | Ground Runs and Test Flights
1.9.1 | Co-ordinate fuel and Test Pilots |  | 27 | 1 | 27 | 1 | 100%
1.9.2 | Perform Ground Runs |  | 27 | 1 | 27 | 1 | 100%
1.9.3 | Perform Track and Balance |  | 27 | 1 | 27 | 1 | 100%
1.9.4 | Perform Maintenance Test Flight |  | 28 | 1 | 28 | 1 | 100%
2.1 | Final Government Inspection and Customer Acceptance
2.1.1 | Government oversight inspects the aircraft and paperwork one last time to ensure all work has been completed in accordance with the project scope |  | 29 | 1 | 29 | 1 | 100%
2.1.2 | Customer Unit inspects the aircraft |  | 29 | 1 | 29 | 1 | 100%
2.1.3 | The aircraft is flown back to its home station |  | 30 | 1 | 30 | 1 | 100%
2.2 | Close work order
2.2.1 | Close work order and file copies of aircraft historical records as proof of maintenance completed. |  | 31 | 2 | 31 | 2 | 100%